## PISIDIMO
Project | Bisidimo River Bridge & Approach Road Project
Span Length | 98m
Location | EAST H/Zone Babile wereda
Client | ORA
Consultant | SG CONSULTING ENGINEERS PLC
Contractor | Level Road Conistruction
Report Month | March
Contract Signed Date | June 28,2019
Commencement Date
Original completion Date | ‎June‎ ‎28‎, ‎2021
Revised completion Date | March 01,2022
Revised Span Length | 84m
Bill No. | Description | Original Contract Amount | Revised Contract Amount | Accomplished up to June 30, 2021/2013 | Previous Months | [7 empty] | % Progress
[7 empty] | This Year todate |  | This Month |  | To Date
[5 empty] | Plan | Accomp | Plan | Accomp | Plan | Accomp | Plan | Accomp | Against Plan | Against Contract | 9000000
1000 | GENERAL PROVISIONS | [10 empty] | 0
2000 | SITE CLEARANCE | [10 empty] | 0
3000 | DRAINAGES | 84000 | [9 empty] | 0
4000 | EARTHWORKS | 6480000 | 3532290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | SUBBASE | 1248750 | 1377036 | 300000 | 0 | 0 | 0 | 0 |  |  | 300000 | 300000
8100 | Foundation for Structures | 7812750 | 7596811.9 | 18602542 | 1424962.981 | 489243.29 | 1424962.981 | 489243.29 |  |  | 34919897.833 | 23737363.184
8200 | Falsework, Formwork, and Concrete Finishes | 1623671.2 | 3611437.6 |  | 1490962.102 | 1011169.394 | 1490962.102 | 1011169.394
8300 | Steel Reinforcement for Structures | 7673500 | 11143800 |  | 1833339.75 | 494339.75 | 1833339.75 | 494339.75
8400 | Concrete for Structures | 4283760 | 8135379 |  | 6598012.5 | 1700068.75 | 6598012.5 | 1700068.75
8700 | Bridge Bearings, Parapets, Railings, etc | 1137775.6 | 890440 |  | 1536000 | 0 | 1536000 | 0
8900 | Stone Masonry Structures | 2968556 |  |  | 3434078.5 | 1440000 | 3434078.5 | 1440000
9000 | ANCILLARY WORKS | 1154700 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| SUB-TOTAL | 34467462.8 | 36287194.5 | 18902542 | 16317355.833 | 5134821.184 | 16317355.833 | 5134821.184 | 0 | 0 | 35219897.833 | 24037363.184 | 68.25% | 66.24%
| 15% VAT. | 5170119.42 | 5443079.175 | 2835381.3 | 2447603.375 | 770223.1776 | 2447603.375 | 770223.1776 | 0 | 0 | 5282984.6749 | 3605604.4776
| GRAND TOTAL | 39637582.22 | 41730273.675 | 21737923.3 | 18764959.2079 | 5905044.3616 | 18764959.2079 | 5905044.3616 | 0 | 0 | 40502882.508 | 27642967.6616
| Percentage |  |  | 52.09% | 44.97% | 14.15% | 44.97% | 14.15% | 0% | 0% | 97.06% | 66.24%
Performance Analysis
Description |  | Status Figures | Remark |  |  |  | Factor for delay (if any)
Original Contract Time (Cal. Days) |  | 731 | [5 empty] | under ground water disturbance
Extension of time (Cal. Days) |  | 273 | [5 empty] | Delay for investigation approval
Total Contract Time (Cal. days) |  | 1004 | [5 empty] | Lack of conistruction mateal
Time Elapsed t (%) |  | 976
Time Elapsed todate (%) |  | 91.33%
Performance Bond Expiry Date |  | June 25,2022
Advance Guarantee Expiry Date |  | January 21,2022
Slippage To-date from time % |  | -25.09%
Slippage from plan % |  | -2.007%
|  | -30.82% |  |  |  |  | Job Opportunity for Local Community
[8 empty] | Skilled | Un skilled
[7 empty] | MALE | 4 | 40
[7 empty] | FEMALE | 0 | 0
[7 empty] | AMOUNT (ETB) | 60000 | 360000

## Erer
Project: Erer River Bridge & Approach Road Project
Client: Oromia Roads Authority
Consultant: SG Consulting Engineers PLC
Contractor: GEMTA Construction PLC
Location: East Hararge/GURSUM WEREDA
Report month |  | March
Contract signed date- June 28/2019
Current commencement Date
Original Completion Date- June‎ ‎28‎, ‎2021
Revised Completion Date- April 16,2022
S.No | Division No. | Description of Items | Unit | Original Contract Amount | Revised Contract Amount | Accomplished up to June 30, 201 | Previuos month |  | This year to date |  | This Month |  | Todate |  | % Accomplished
[7 empty] | Plan | Accomp | Plan | Accomp | Plan | Accomp | Plan | Accomp | Against Plan | Against Contract
1 | 3400 | PITCHING, STONEWORK AND EROSION PROTECTION | ETB |  | 0 | 0
2 | 4200 | Road way And Borrow Excavation | ETB | 7752150 | 9334564 | 7000000 | 2327680.5 | 0 | 2327680.5 | 0 |  |  | 7000000 | 7000000
3 | 5100 | SUB BASE | ETB | 845250 | 570434.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | 8100 | Foundation for Structures | ETB | 4677837 | 4703375 | 5743475 | 0 | 0 | 0 | 0 |  |  | 5743475 | 5743475
5 | 8200 | Falsework, Formwork, and Concrete Finishes | ETB | 1514250 | 1450800 | 1000000 | 1137720 | 330000 | 1514250 | 490000 | 376530 | 160000 | 1490000 | 1490000
6 | 8300 | Steel Reinforcement for Structures | ETB | 4607880 | 3351600 | 2000000 | 583760 | 0 | 1033760 | 360000 | 450000 | 360000 | 2360000 | 2360000
7 | 8400 | Concrete for Structures | ETB | 3081650 | 1802900 | 1800000 | 104775 | 0 | 1455775 | 250000 | 1351000 | 250000 | 2050000 | 2050000
8 | 8700 | Bridge Bearings, Parapets, Railings, etc | ETB | 1010200 | 1254672 | 0 | 1296000 | 220000 | 1296000 | 220000 |  |  | 220000 | 220000
9 | 8900 | Stone Masonry Structures | ETB | 3240720 | 5237550 | 5250000 | 0 | 0 | 0 | 220000 |  |  | 5470000 | 5470000
10 | 9100 | Ancillary Works | ETB | 7862000 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
Total |  |  | ETB | 34591937 | 27705895.5 | 22793475 | 5449935.5 | 550000 | 7627465.5 | 1540000 | 2177530 | 770000 | 24333475 | 24333475 | 100% | 87.83%
15% VAT |  |  | ETB | 5188790.55 | 4155884.325 | 3419021.25 | 817490.325 | 82500 | 1144119.825 | 231000 | 326629.5 | 115500 | 3650021.25 | 3650021.25
Grand Total |  |  | ETB | 39780727.55 | 31861779.825 | 26212496.25 | 6267425.825 | 632500 | 8771585.325 | 1771000 | 2504159.5 | 885500 | 27983496.25 | 27983496.25
|  |  | Percentage |  |  | 65.89% | 15.75% | 1.985% | 27.53% | 5.558% | 7.859% | 2.779% | 87.83%
|  | Performance Analysis |  |  |  |  | Job Opportunity for Local Community |  |  |  | Factor for delay (if any) | Slope Excavation is done to safe work
|  | Description |  | Status Figures | Remark | [6 empty] | Insecurity Problems
|  | Original Contract Time (Cal. Days) |  | 731 |  |  |  | Skilled | Unskilled |  |  | Rain and flood
|  | Extension of time (Cal. Days) |  | 302 |  |  | MALE | 5 | 14 |  |  | Redesign and investigation
|  | Total Contract Time (Cal. days) |  | 1033 |  |  | FEMALE | 0 | 6
|  | Time Elapsed t (%) |  | 94.48% |  |  | AMOUNT (ETB) | 75000 | 180000
|  | Time Elapsed todate (%) |  | 976
|  | Performance Bond Expiry Date |  | June‎ ‎19‎, ‎2022
|  | Advance Guarantee Expiry Date |  | March 03,2022
|  | Slippage To-date from time % |  | -6.654%
|  | Slippage from plan % |  | 0%

## HOSE
Project: | HOSE River Bridge & Approach Road Project
Client: Oromia Roads Authority
Consultant: SG Consulting Engineers PLC
Contractor: GEMTA Construction PLC
Location: East Hararge/GURSUM WEREDA
Report month |  | March
Contract signed date- June 28/2019
Current commencement Date
Original Completion Date- June‎ ‎28‎, ‎2021
Revised Completion Date- April 16,2022
S.No | Division No. | Description of Items | Unit | Original Contract Amount | Revised Contract Amount | Accomplished up to June 30, 2021 | Previuos month |  | This year to date |  | This Month |  | Todate |  | % Accomplished
[7 empty] | Plan | Accomp | Plan | Accomp | Plan | Accomp | Plan | Accomp | Against Plan | Against Contract
1 | 3400 | PITCHING, STONEWORK AND EROSION PROTECTION | ETB
2 | 4200 | Road way And Borrow Excavation | ETB | 8820000 | 7761016.5 | 2200000 | 7225045 | 470000 | 7225045 | 470000 |  |  | 9425045 | 2670000
3 | 5100 | SUB BASE | ETB | 1164375 | 1505350 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4 | 8100 | Foundation for Structures | ETB | 5018721 | 3800575 | 8840675 | 0 | 0 | 0 | 0 |  |  | 8840675 | 8840675
5 | 8200 | Falsework, Formwork, and Concrete Finishes | ETB | 1649304 | 1754154 | 1500000 | 830556 | 285000 | 830556 | 435000 |  | 150000 | 2330556 | 1935000
6 | 8300 | Steel Reinforcement for Structures | ETB | 5814000 | 4073600 | 1000000 | 82080 | 0 | 82080 | 0 | 1200000 |  | 1082080 | 1000000
7 | 8400 | Concrete for Structures | ETB | 3275765 | 1915100 | 1000000 | 95975 | 0 | 95975 | 0 |  |  | 1095975 | 1000000
8 | 8700 | Bridge Bearings, Parapets, Railings, etc | ETB | 1608505 | 1109270 | 0 | 540000 | 0 | 540000 | 0 |  |  | 540000 | 0
9 | 8900 | Stone Masonry Structures | ETB | 4386105 | 4222800 | 3000000 | 0 | 0 | 0 | 0 |  |  | 3000000 | 3000000
10 | 9100 | Ancillary Works | ETB | 808028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  | ETB | 32544803 | 26141865.5 | 17540675 | 8773656 | 755000 | 9973656 | 905000 | 1200000 | 150000 | 26314331 | 18445675 | 70.1% | 70.56%
15% VAT |  |  | ETB | 4881720.45 | 3921279.825 | 2631101.25 | 30000 | 113250 | 210000 | 135750 | 180000 | 22500 | 3947149.65 | 2653601.25
Grand Total |  |  | ETB | 37426523.45 | 30063145.325 | 20171776.25 | 230000 | 868250 | 1610000 | 1040750 | 1380000 | 172500 | 30261480.65 | 20344276.25
|  |  | Percentage |  |  | 67.1% | 33.56% | 2.888% | 38.15% | 3.462% | 4.59% | 0.0057379 | 80.86% | 70.56%
Performance Analysis
|  | Description |  | Status Figures | Remark |  | Factor for delay (if any) |  |  |  | Job Opportunity for Local Community
|  | Original Contract Time (Cal. Days) |  | 731 |  |  |  | access road problem
|  | Extension of time (Cal. Days) |  | 302 |  |  |  | Insecurity Problems |  |  |  | Skilled | Unskilled
|  | Total Contract Time (Cal. days) |  | 1033 |  |  |  | Capacity of contructor |  |  | MALE | 5 | 14
|  | Time Elapsed t (%) |  | 94.48% |  |  |  | Insecurity Problems |  |  | FEMALE | 0 | 6
|  | Time Elapsed todate (%) |  | 976 |  |  |  | Rain and flood |  |  | AMOUNT (ETB) | 75000 | 180000
|  | Performance Bond Expiry Date |  | June‎ ‎19‎, ‎2022 |  |  |  | Foundation investigation
|  | Advance Guarantee Expiry Date |  | March 03,2022
|  | Slippage To-date from time % |  | -23.92%
|  | Slippage from plan % |  | -10.3%

## bosha (hidden)
Project | BOSHA BRIDGE
Span Length | 29M
Location | WEST H/Zone HABRO wereda
Client | ORA
Consultant | SG CONSULTING ENGINEERS PLC |  |  | Provisionally handed over to the client
Contractor | ORCE
Report Month | March
Contract Signed Date | FEBRUARY 16/2018 GC
Commencement Date
Original completion Date | FEBRUARY 16/2020 GC
Revised completion Date
Revised Span Length | 29m
Bill No. | Description | Original Contract Amount | Revised Contract Amount | Accomplished up to June 30, 2021 | Previous Months | [7 empty] | % Progress
[7 empty] | This Year todate |  | This Month |  | To Date
[5 empty] | Plan | Accomp | Plan | Accomp | Plan | Accomp | Plan | Accomp | Against Plan | Against Contract
1000 | GENERAL PROVISIONS | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2000 | SITE CLEARANCE | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3000 | DRAINAGES |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4000 | EARTHWORKS | 1350000 |  | 1714242 | 0 | 0 | 0 | 0 |  |  | 1714242 | 1714242
5000 | SUBBASE | 117600 |  | 0 | 131913.6 | 0 | 131913.6 | 0 |  |  | 131913.6 | 131913.6
8000 | STRUCTURES | 10616899.3698 |  | 6734324.7464 | 1700000 | 1700000 | 1700000 | 1700000 |  |  | 8434324.7464 | 8434324.7464
9000 | ANCILLARY WORKS | 225609.7283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SUB-TOTAL | 12310109.0981 |  | 8448566.7464 | 1700000 | 1700000 | 1831913.6 | 1700000 | 0 | 0 | 10280480.3464 | 10280480.3464 | 100% | 83.51%
| 15% VAT. | 1846516.3647 |  | 1267285.012 | 255000 | 255000 | 274787.04 | 255000 | 0 | 0 | 1542072.052 | 1542072.052
| GRAND TOTAL | 14156625.4628 |  | 9715851.7583 | 1955000 | 1955000 | 2106700.64 | 1955000 | 0 | 0 | 11822552.3983 | 11822552.3983
| Percentage |  |  | 68.63% | 13.81% | 13.81% | 14.88% | 13.81% | 0% | 0% | 83.51% | 83.51%
Performance Analysis
Description |  | Status Figures | Remark |  |  |  | Factor for delay (if any) | Capasity of contractor
Original Contract Time (Cal. Days) |  | 731 | [5 empty] | investigation apprival
Extension of time (Cal. Days) |  | 238 | [5 empty] | lack of material and man power supply
Total Contract Time (Cal. days) |  | 969 | [5 empty] | Capasity of contractor
Time Elapsed t (%) | [7 empty] | Rain and flood
Time Elapsed todate (%) | [7 empty] | Foundation investigation
Performance Bond Expiry Date
Advance Guarantee Expiry Date
Slippage To-date from time %
Slippage from plan %
Job Opportunity for Local Community
[8 empty] | Skilled | Un skilled
MALE
FEMALE
AMOUNT (ETB)

## H;GOLOBA (hidden)
Project | HARO GOLOBA BRIDGE
Span Length | 24M
Location | WEST H/Zone GEMECHIS wereda
Client | ORA |  |  |  |  | Provisionally handed over to the client
Consultant | SG CONSULTING ENGINEERS PLC
Contractor | ORCE
Report Month | March
Contract Signed Date | FEBRUARY 16/2018 GC
Commencement Date
Original completion Date | FEBRUARY 16/2018 GC
Revised completion Date
Revised Span Length | 14
Bill No. | Description | Original Contract Amount | Revised Contract Amount | Accomplished up to June 30, 2021 | Previous Months | [7 empty] | % Progress
[7 empty] | This Year todate 2013 |  | This Month |  | To Date
[5 empty] | Plan | Accomp | Plan | Accomp | Plan | Accomp | Plan | Accomp | Against Plan | Against Contract
1000 | GENERAL PROVISIONS | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2000 | SITE CLEARANCE | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3000 | DRAINAGES |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4000 | EARTHWORKS | 1350000 |  | 1200000 | 0 | 0 | 0 | 0 |  |  | 1200000 | 1200000
5000 | SUBBASE | 117600 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8000 | STRUCTURES | 10629615.6706 |  | 7711113.7512 | 3800000 | 3800000 | 3800000 | 3800000 | 0 | 0 | 11511113.7512 | 11511113.7512
9000 | ANCILLARY WORKS | 239696.9565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| SUB-TOTAL | 12336912.6271 |  | 8911113.7512 | 3800000 | 3800000 | 8601083.2 | 5701083.2 | 0 | 0 | 17512196.9512 | 12711113.7512 | 72.58% | 103%
| 15% VAT. | 1850536.8941 |  | 1336667.0627 | 570000 | 570000 | 1290162.48 | 855162.48 | 0 | 0 | 2626829.5427 | 1906667.0627
| GRAND TOTAL | 14187449.5211 |  | 10247780.8139 | 4370000 | 4370000 | 9891245.68 | 6556245.68 | 0 | 0 | 20139026.4939 | 14617780.8139
| Percentage |  |  | 72.23% | 30.8% | 30.8% | 69.72% | 46.21% | 0% | 0% | 141.9% | 103%
Performance Analysis
Description |  | Status Figures | Remark |  |  |  | Factor for delay (if any) | Capasity of contractor
Original Contract Time (Cal. Days) |  | 371 | [5 empty] | investigation apprival
Extension of time (Cal. Days) |  | 275 | [5 empty] | lack of material and man power supply
Total Contract Time (Cal. days) |  | 646 | [5 empty] | Capasity of contractor
Time Elapsed t (%) | [7 empty] | Rain and flood
Time Elapsed todate (%) | [7 empty] | Foundation investigation
Performance Bond Expiry Date
Advance Guarantee Expiry Date
Slippage To-date from time %
Slippage from plan %
Job Opportunity for Local Community
[8 empty] | Skilled | Un skilled
MALE
FEMALE
AMOUNT (ETB)

## CHAFE RAMIS (hidden)
Project | CHEFE RAMIS BRIDGE
Span Length | 20M
Location | EAST H/Zone META wereda
Client | ORA
Consultant | SG CONSULTING ENGINEERS PLC
Contractor | ORCE
Report Month | March |  |  |  | Provisionally handed over to the client
Contract Signed Date | FEBRUARY 16/2018 GC
Commencement Date
Original completion Date | FEBRUARY 16/2020 GC
Revised completion Date
Revised Span Length
Bill No. | Description | Original Contract Amount | Revised Contract Amount | Accomplished up to June 30, 2021 | Previous Months | [7 empty] | % Progress
[7 empty] | This Year todate |  | This Month |  | To Date
[5 empty] | Plan | Accomp | Plan | Accomp | Plan | Accomp | Plan | Accomp | Against Plan | Against Contract
1000 | GENERAL PROVISIONS
2000 | SITE CLEARANCE
3000 | DRAINAGES |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4000 | EARTHWORKS | 1428500 |  | 1051610.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1051610.5 | 1051610.5
5000 | SUBBASE | 131250 |  | 0 | 137410 | 137410 | 137410 | 137410 |  |  | 137410 | 137410
8000 | STRUCTURES | 7953829.7665 |  | 5760030.5512 | 1244169.1006 | 1244169.1006 | 1244169.1006 | 1244169.1006 |  |  | 7004199.6518 | 7004199.6518
9000 | ANCILLARY WORKS | 229214.6739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SUB-TOTAL | 9742794.4404 |  | 8120030.5512 | 1244169.1006 | 1244169.1006 | 10553829 | 6130000 | 0 | 0 | 8193220.1518 | 8193220.1518 | 100% | 84.1%
| 15% VAT. | 1461419.1661 |  | 1218004.5827 | 186625.3651 | 186625.3651 | 1583074.35 | 919500 | 0 | 0 | 1228983.0228 | 1228983.0228
| GRAND TOTAL | 11204213.6065 |  | 9338035.1339 | 1430794.4657 | 1430794.4657 | 12136903.35 | 7049500 | 0 | 0 | 9422203.1746 | 9422203.1746
| Percentage |  |  | 83.34% | 12.77% | 12.77% | 108.3% | 62.92% | 0% | 0% | 84.1% | 84.1%
Performance Analysis
Description |  | Status Figures | Remark |  |  |  | Factor for delay (if any) | Capasity of contractor
Original Contract Time (Cal. Days) |  | 371 | [5 empty] | investigation apprival
Extension of time (Cal. Days) |  | 262 | [5 empty] | lack of material and man power supply
Total Contract Time (Cal. days) |  | 633 | [5 empty] | Capasity of contractor
Time Elapsed t (%) | [7 empty] | Rain and flood
Time Elapsed todate (%) | [7 empty] | Foundation investigation
Performance Bond Expiry Date
Advance Guarantee Expiry Date
Slippage To-date from time %
Slippage from plan %
Job Opportunity for Local Community
[8 empty] | Skilled | Un skilled
MALE
FEMALE
AMOUNT (ETB)

## GUDA
Project | GUDA BRIDGE
Span Length | 36M
Location | WEST H/Zone HABRO wereda
Client | ORA
Consultant | SG CONSULTING ENGINEERS PLC
Contractor | BIRBO CONISTRUCTION PLC
Report Month | March
Contract Signed Date | JUNE 28/2019 GC
Commencement Date
Original completion Date | ‎June‎ ‎28‎, ‎2021
Revised completion Date
Revised Span Length | 36M
Bill No. | Description | Original Contract Amount | Revised Contract Amount | Accomplished up to June 30, 2021 | Previous Months | [7 empty] | % Progress
[7 empty] | This Year todate |  | This Month |  | To Date
[5 empty] | Plan | Accomp | Plan | Accomp | Plan | Accomp | Plan | Accomp | Against Plan | Against Contract
1000 | GENERAL PROVISIONS | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2000 | SITE CLEARANCE | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3000 | DRAINAGES | 351360 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
4000 | EARTHWORKS | 2000000 | 2000000 | 980000 | 100000 | 100000 | 100000 | 100000 |  |  | 1080000 | 1080000
5000 | SUBBASE | 262500 | 262500 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0
8100 | Foundation for Structures | 17651451 | 13125859 | 11850000 | 65000 | 65000 | 65000 | 65000 |  |  | 13234500 | 15401000
8200 | Falsework, Formwork, and Concrete Finishes |  |  |  | 416000 | 416000 | 416000 | 416000
8300 | Steel Reinforcement for Structures |  |  |  |  | 0 | 0 | 0
8400 | Concrete for Structures |  |  |  |  | 0 | 750000 | 450000 | 750000 | 450000
8700 | Bridge Bearings, Parapets, Railings, etc |  |  |  |  | 0 | 0 | 0
8900 | Stone Masonry Structures |  |  |  | 218500 | 2620000 | 218500 | 2620000
9000 | ANCILLARY WORKS | 2424150 | 125000 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| SUB-TOTAL | 22689461 | 15513359 | 12830000 | 799500 | 3201000 | 1549500 | 3651000 | 750000 | 450000 | 14314500 | 16481000 | 115.1% | 72.64%
| 15% VAT. | 3403419.15 | 2327003.85 | 1924500 | 119925 | 480150 | 232425 | 547650 | 112500 | 67500 | 2147175 | 2472150
| GRAND TOTAL | 26092880.15 | 17840362.85 | 14754500 | 919425 | 3681150 | 1781925 | 4198650 | 862500 | 517500 | 16461675 | 18953150
| Percentage |  |  | 56.55% | 3.524% | 14.11% | 6.829% | 16.09% | 3.305% | 1.983% | 63.09% | 72.64%
Performance Analysis
Description |  | Status Figures | Remark |  |  |  | Factor for delay (if any)
Original Contract Time (Cal. Days) |  | 731 | [5 empty] | INSECURITY
Extension of time (Cal. Days) |  | 289 | [5 empty] | INVESTIGATION APOVAL DELAY
Total Contract Time (Cal. days) |  | 1020 | [5 empty] | CONTRACTORS CAPACITY
Time Elapsed t (%) |  | 95.69% | [5 empty] | ACCESS AND RIGHT OF WAY
Time Elapsed todate (%) |  | 976 | [5 empty] | CONTRACTORS CAPACITY
Performance Bond Expiry Date | [7 empty] | Rain and flood
Advance Guarantee Expiry Date
Slippage To-date from time % |  | -23.05%
Slippage from plan % |  | 9.548%
Job Opportunity for Local Community
[8 empty] | Skilled | Un skilled
[7 empty] | MALE | 5 | 15
[7 empty] | FEMALE |  | 10
AMOUNT (ETB)

## CHAFE
Project | CHAFE BRIDGE
Span Length | 30M
Location | WEST H/Zone HABRO wereda
Client | ORA
Consultant | SG CONSULTING ENGINEERS PLC
Contractor | BIRBO CONISTRUCTION PLC
Report Month | March
Contract Signed Date | JUNE 28/2019 GC
Commencement Date
Original completion Date | ‎June‎ ‎28‎, ‎2021
Revised completion Date
Revised Span Length | 30M
Bill No. | Description | Original Contract Amount | Revised Contract Amount | Accomplished up to June 30, 2021 | Previous Months | [7 empty] | % Progress
[7 empty] | This Year todate |  | This Month |  | To Date
[5 empty] | Plan | Accomp | Plan | Accomp | Plan | Accomp | Plan | Accomp | Against Plan | Against Contract
1000 | GENERAL PROVISIONS | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2000 | SITE CLEARANCE | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3000 | DRAINAGES |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4000 | EARTHWORKS |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5000 | SUBBASE |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8100 | Foundation for Structures | 9425779 | 13663877 | 8000000 | 152000 | 70000 | 152000 | 70000 |  |  | 13674500 | 8872500
8200 | Falsework, Formwork, and Concrete Finishes |  |  |  | 608000 | 502500 | 608000 | 802500 |  | 300000
8300 | Steel Reinforcement for Structures |  |  |  | 2080000 | 120000 | 2080000 | 120000
8400 | Concrete for Structures |  |  |  | 685000 | 0 | 685000 | 0
8700 | Bridge Bearings, Parapets, Railings, etc |  |  |  | 2000000 | 0 | 2000000 | 0
8900 | Stone Masonry Structures |  |  |  | 149500 | 0 | 149500 | 0
9000 | ANCILLARY WORKS | 4583700 | 125000 | 0 | 0 | 0 | 125000 | 0 | 125000 |  | 125000 | 0 | 0.027271
| SUB-TOTAL | 14009479 | 13788877 | 8000000 | 5674500 | 692500 | 5799500 | 992500 | 125000 | 300000 | 13799500 | 8872500 | 64.3% | 63.33%
| 15% VAT. | 2101421.85 | 2068331.55 | 1200000 | 851175 | 103875 | 869925 | 148875 | 18750 | 45000 | 2069925 | 1245000
| GRAND TOTAL | 16110900.85 | 15857208.55 | 9200000 | 6525675 | 796375 | 6669425 | 1141375 | 143750 | 345000 | 15869425 | 9545000
| Percentage |  |  | 57.1% | 40.5% | 4.943% | 41.4% | 7.084% | 0.9065% | 3.75% | 98.5% | 63.33%
Performance Analysis
Description |  | Status Figures | Remark |  |  |  | Factor for delay (if any)
Original Contract Time (Cal. Days) |  | 731 | [5 empty] | INSECURITY
Extension of time (Cal. Days) |  | 289 | [5 empty] | INVESTIGATION APOVAL DELAY
Total Contract Time (Cal. days) |  | 1020 | [5 empty] | CONTRACTORS CAPACITY
Time Elapsed t (%) |  | 95.69% | [5 empty] | ACCESS AND RIGHT OF WAY
Time Elapsed todate (%) |  | 976 | [5 empty] | CONTRACTORS CAPACITY
Performance Bond Expiry Date | [7 empty] | Rain and flood
Advance Guarantee Expiry Date | [7 empty] | redesign and investigation
Slippage To-date from time % |  | -32.35%
Slippage from plan % |  | -35.17%
Job Opportunity for Local Community
[8 empty] | Skilled | Un skilled
[7 empty] | MALE | 4 | 16
[7 empty] | FEMALE |  | 6
[7 empty] | AMOUNT (ETB) | 60000 | 176000

## DHAMAE
Project | Dhamae River Bridge
Span Length | 30M
Location | WEST H/Zone
Client | ORA
Consultant | SG CONSULTING ENGINEERS PLC
Contractor | BIRBO CONISTRUCTION PLC
Report Month | March
Contract Signed Date | JUNE 28/2019 GC
Commencement Date
Original completion Date | ‎June‎ ‎28‎, ‎2021
Revised completion Date
Revised Span Length | 30M
Bill No. | Description | Original Contract Amount | Revised Contract Amount | Accomplished up to June 30, 2020 | Previous Months | [7 empty] | % Progress
[7 empty] | This Year todate |  | This Month |  | To Date
[5 empty] | Plan | Accomp | Plan | Accomp | Plan | Accomp | Plan | Accomp | Against Plan | Against Contract
1000 | GENERAL PROVISIONS |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2000 | SITE CLEARANCE |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3000 | DRAINAGES |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4000 | EARTHWORKS |  |  | 0 | 1193700 | 0 | 1193700 | 0 |  |  | 1193700 | 0
5000 | SUBBASE |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8100 | Foundation for Structures |  |  |  | 220482 | 250000 | 220482 | 250000 |  |  | 220482 | 250000
8200 | Falsework, Formwork, and Concrete Finishes |  |  |  | 64000 | 64000 | 64000 | 64000 |  |  | 64000 | 64000
8300 | Steel Reinforcement for Structures |  |  |  | 396500 | 396500 | 396500 | 396500 |  |  | 396500 | 396500
8400 | Concrete for Structures |  |  |  | 725000 | 659090.9091 | 725000 | 659090.9091 |  |  | 725000 | 659090.9091
8700 | Bridge Bearings, Parapets, Railings, etc |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0
8900 | Stone Masonry Structures |  |  |  | 2829000 | 1626500 | 2829000 | 1626500 |  |  | 2829000 | 1626500
9000 | ANCILLARY WORKS |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 19726790.48
| SUB-TOTAL |  |  | 0 | 5428682 | 2996090.9091 | 5428682 | 2996090.9091 | 0 | 0 | 5428682 | 2996090.9091 | 55.19% | 15.19%
| 15% VAT. | 0 |  |  | 814302.3 | 449413.6364 | 814302.3 | 449413.6364 | 0 | 0 | 814302.3 | 449413.6364
| GRAND TOTAL | 0 |  |  | 6242984.3 | 3445504.5455 | 6242984.3 | 3445504.5455 | 0 | 0 | 6242984.3 | 3445504.5455
| Percentage |  |  |  | 27.52% | 15.19% | 27.52% | 15.19% | 0% | 0% | 27.52% | 15.19%
Performance Analysis
Description |  | Status Figures | Remark |  |  |  | Factor for delay (if any) | Replecment of bridge
Original Contract Time (Cal. Days) |  | 731 | [5 empty] | Acess road problem
Extension of time (Cal. Days) |  | 289
Total Contract Time (Cal. days) |  | 1020
Time Elapsed t (%) |  | 95.69%
Time Elapsed todate (%) |  | 976
Performance Bond Expiry Date
Advance Guarantee Expiry Date
Slippage To-date from time % |  | -80.5%
Slippage from plan % |  | -12.33%
Job Opportunity for Local Community
[8 empty] | Skilled | Un skilled
[7 empty] | MALE | 4 | 26
[7 empty] | FEMALE | 1 | 12
[7 empty] | AMOUNT (ETB) | 0 | 0

## BURKA
Project | BURKA BRIDGE
Span Length | 26M
Location | EAST H/Zone DEDER wereda
Client | ORA
Consultant | SG CONSULTING ENGINEERS PLC
Contractor | ROBSEN B.A CONSTRUCTION
Report Month | March
Contract Signed Date | FEB 17/2020 GC
Commencement Date
Original completion Date | AUGEST 10/2021 GC
Revised completion Date | Feb 10/2022 GC
Revised Span Length | 26M
Bill No. | Description | Original Contract Amount | Revised Contract Amount | Accomplished up to June 30, 2021 | Previous Months | [7 empty] | % Progress
[7 empty] | This Year todate(2013) |  | This Month |  | To Date
[5 empty] | Plan | Accomp | Plan | Accomp | Plan | Accomp | Plan | Accomp | Against Plan | Against Contract
1000 | GENERAL PROVISIONS
2000 | SITE CLEARANCE
3000 | DRAINAGES |  | 206280 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
4000 | EARTHWORKS |  | 2184000 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5000 | SUBBASE |  | 266000 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8000 | STRUCTURES |  | 13344683 | 700000 | 5140000 | 3570000 | 5640000 | 3720000 | 500000 | 150000 | 6340000 | 4420000
9000 | ANCILLARY WORKS |  | 3271800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SUB-TOTAL |  | 19272763 | 700000 | 5140000 | 3570000 | 5640000 | 3720000 | 500000 | 150000 | 6140000 | 4420000 | 71.99% | 22.93%
| 15% VAT. | 0 | 2890914.45 | 105000 | 771000 | 846000 | 846000 | 558000 | 75000 | 22500 | 921000 | 663000
| GRAND TOTAL | 0 | 22163677.45 | 805000 | 5911000 | 4416000 | 6486000 | 4278000 | 575000 | 172500 | 7061000 | 5083000
| Percentage |  |  | 3.632% | 26.67% | 18.52% | 29.26% | 19.3% | 2.594% | 0.7783% | 31.86% | 22.93%
Performance Analysis
Description |  | Status Figures | Remark |  |  |  | Factor for delay (if any)
Original Contract Time (Cal. Days) |  | 540
Extension of time (Cal. Days) |  | 181 | [5 empty] | ACCESS ROAD PROBLEM
Total Contract Time (Cal. days) |  | 721 | [5 empty] | BID APOROVAL
Time Elapsed t (%) |  | 102.9%
Time Elapsed todate (%) |  | 742
Performance Bond Expiry Date |  | September 04,2022
Advance Guarantee Expiry Date
Slippage To-date from time % |  | -79.98%
Slippage from plan % |  | -8.925%
Job Opportunity for Local Community
[8 empty] | Skilled | Un skilled
[7 empty] | MALE | 4 | 26
[7 empty] | FEMALE | 1 | 12
[7 empty] | AMOUNT (ETB) | 0 | 0

## TOGO
Project | TOGO BRIDGE
Span Length | 35M
Location | WEST H/Zone MIESO wereda
Client | ORA
Consultant | SG CONSULTING ENGINEERS PLC
Contractor | ROBSEN B.A CONSTRUCTION
Report Month | March
Contract Signed Date | JUNE 1/2020 GC
Commencement Date
Original completion Date | JUNE 27/2022 GC
Revised completion Date | JUNE 27/2022 GC
Revised Span Length | 35M
Bill No. | Description | Rvised Contract Amount | Original Contract Amount | Accomplished up to June 30, 2021 | Previous Months | [7 empty] | % Progress
[7 empty] | This Year todate |  | This Month |  | To Date
[5 empty] | Plan | Accomp | Plan | Accomp | Plan | Accomp | Plan | Accomp | Against Plan | Against Contract
1000 | GENERAL PROVISIONS | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
2000 | SITE CLEARANCE | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
3000 | DRAINAGES | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 21684570.315
4000 | EARTHWORKS | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
5000 | SUBBASE | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
8000 | STRUCTURES | 15179621.2092 | 15498848.1 | 7059521.28 | 3210000 | 625000 | 3210000 | 625000 |  |  | 10269521.28 | 7684521.28
9000 | ANCILLARY WORKS | 0 | 3357300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SUB-TOTAL | 15179621.2092 | 18856148.1 | 7059521.28 | 3210000 | 625000 | 3210000 | 7059521.28 | 0 | 0 | 10269521.28 | 7684521.28 | 74.83% | 40.75%
| 15% VAT. | 2276943.1814 | 2828422.215 | 1058928.192 | 481500 | 93750 | 481500 | 1058928.192 | 0 | 0 | 1540428.192 | 1152678.192
| GRAND TOTAL | 17456564.3906 | 21684570.315 | 8118449.472 | 3691500 | 718750 | 3691500 | 8118449.472 | 0 | 0 | 11809949.472 | 8837199.472
| Percentage |  |  | 37.44% | 17.02% | 3.315% | 17.02% | 37.44% | 0% | 0% | 54.46% | 40.75%
Performance Analysis
Description |  | Status Figures | Remark |  |  |  | Factor for delay (if any)
Original Contract Time (Cal. Days) |  | 540
Extension of time (Cal. Days) |  | 181 | [5 empty] | GEOTECHNICAL INVESTIGATION |  |  | There is no major progress due to right of way problem …
Total Contract Time (Cal. days) |  | 721 | [5 empty] | BID APOROVAL
Time Elapsed t (%) |  | 102.9% | [5 empty] | Right of way
Time Elapsed todate (%) |  | 742
Performance Bond Expiry Date | [7 empty] | Rain and flood
Advance Guarantee Expiry Date
Slippage To-date from time % |  | -62.16%
Slippage from plan % |  | -13.71%
Job Opportunity for Local Community
[8 empty] | Skilled | Un skilled
[7 empty] | MALE | 4 | 26
[7 empty] | FEMALE | 1 | 12
[7 empty] | AMOUNT (ETB) | 0 | 0

## santala
Project | Santela River Bridge & Approach Road Project
Span Length | DESIGN IS SUBMITED FOR APPROVAL
Location
Client
Consultant
Contractor
Report Month
Contract Signed Date
Commencement Date
Original completion Date
Revised completion Date
Revised Span Length
Bill No. | Description | Original Contract Amount | Revised Contract Amount | Accomplished up to June 30, 2020 | Previous Months | [7 empty] | % Progress
[7 empty] | This Year todate |  | This Month |  | To Date
[5 empty] | Plan | Accomp | Plan | Accomp | Plan | Accomp | Plan | Accomp | Against Plan | Against Contract
1000 | GENERAL PROVISIONS |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
2000 | SITE CLEARANCE |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3000 | DRAINAGES |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
4000 | EARTHWORKS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | SUBBASE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | STRUCTURES |  |  | 0 | 0 | 0
9000 | ANCILLARY WORKS |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SUB-TOTAL |  |  | 0 | 0 | 0
| 15% VAT. | 0 |  |  | 0 | 0
| GRAND TOTAL | 0 |  |  | 0 | 0
Percentage
Performance Analysis
Description |  | Status Figures | Remark |  |  |  | Factor for delay (if any)
Original Contract Time (Cal. Days)
Extension of time (Cal. Days) | [10 empty] | the contarctor is engaged in massonery stone production
Total Contract Time (Cal. days)
Time Elapsed t (%)
Time Elapsed todate (%)
Performance Bond Expiry Date
Advance Guarantee Expiry Date
Slippage To-date from time %
Slippage from plan %
Job Opportunity for Local Community
[8 empty] | Skilled | Un skilled
[7 empty] | MALE | 0 | 0
FEMALE
[7 empty] | AMOUNT (ETB) | 0 | 0

## Burka Hirna
Project | Burqa River Bridge & Approach Road Project
Span Length | Contractor is terminated and it's in Rebid Process
Location
Client
Consultant
Contractor
Report Month
Contract Signed Date
Commencement Date
Original completion Date
Revised completion Date
Revised Span Length
Bill No. | Description | Original Contract Amount | Revised Contract Amount | Accomplished up to June 30, 2020 | Previous Months | [7 empty] | % Progress
[7 empty] | This Year todate |  | This Month |  | To Date
[5 empty] | Plan | Accomp | Plan | Accomp | Plan | Accomp | Plan | Accomp | Against Plan | Against Contract
1000 | GENERAL PROVISIONS |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
2000 | SITE CLEARANCE |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3000 | DRAINAGES |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
4000 | EARTHWORKS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | SUBBASE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | STRUCTURES |  |  | 0 | 0 | 0
9000 | ANCILLARY WORKS |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SUB-TOTAL |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0
| 15% VAT. | 0 |  |  | 0 | 0
| GRAND TOTAL | 0 |  |  | 0 | 0
Percentage
Performance Analysis
Description |  | Status Figures | Remark |  |  |  | Factor for delay (if any)
Original Contract Time (Cal. Days)
Extension of time (Cal. Days)
Total Contract Time (Cal. days)
Time Elapsed t (%)
Time Elapsed todate (%)
Performance Bond Expiry Date
Advance Guarantee Expiry Date
Slippage To-date from time %
Slippage from plan %
Job Opportunity for Local Community
[8 empty] | Skilled | Un skilled
[7 empty] | MALE | 0 | 0
FEMALE
[7 empty] | AMOUNT (ETB) | 0 | 0